## Slide 1: Joint GoL/WB Portfolio Review Rural and Renewable Energy Agency Ministerial Complex November 8, 2022

## Slide 2: Overview- Project # 1: Liberia Renewable Energy Access Project
Supports the construction of Kaiha 2 mini-grid comprising of a 2.5MW hydropower power plant, 1.8MW diesel power plant (back-up), 33/0.4kV distribution network including 10,000 service connections in Lofa (Voinjama, Foya, Kolahun, Massambolahun, Bolahun & surrounding areas), and the market development of stand-alone solar systems Closing date: December 31, 2023, revised from June 30, 2021 Funding: US$ 27.00 mil (US$25mil- grant, US$2 mil – IDA Loan) Expected Outcome: i) 50,000 people from decentralized electricity; 100,000 people from standalone solar systems; ii) Annual electricity generated - 13.14 GWh/year

## Slide 3: Overview- Project #2-Off-grid component of Liberia Energy Sector Strengthening and Access Project
Funds the electrification of rural health centers, and electrification of households in off-grid areas via the deployment of mini-grid solar PV/battery - diesel mini-grids and Solar Home Systems (SHS).
Closing date: December 31, 2025, revised from June 30, 2021
Funding: US$ 9.20 mil (US$ 7.2mil - grant, US$2 mil – IDA Loan)
Expected Outputs: 189 health centers electrified (in phases); 6,000 household electrified through SHS; 500 connections via mini-grid.
Expected Outcome: 32,500 people provided with electricity off-grid component of the Liberia Energy Sector Strengthening and Access Project (LESSAP)

## Slide 4: Shared Goal/Objectives:
To increase access to electricity and to foster the use of renewable energy sources

## Slide 5: Project # 1: Liberia Renewable Energy Access Project – ongoing, about 60% complete
Compensation to project affected persons completed. Bidding for the construction of 1.8MW diesel plant near conclusion. Construction of 2.5MW hydropower plant & 33/0.4kV distribution network underway. Specifically, Designs for the hydropower plant being finalized; designs for 33/0.4kV distribution network completed About 50% of equipment/materials for the 33/0.4kV distribution network supplied Installation works for the distribution network ongoing. Construction of basic infrastructures on the hydropower site is substantially completed Preparatory construction works (excavation, etc.) for the main components of hydropower plant ongoing

## Slide 6: Project # 1: Liberia Renewable Energy Access Project – ongoing, about 60% complete cont’d
Market development of stand-alone systems: 166,127 people with access to modern energy services/ SHS Executive Order # 107 issued: suspends import duty on quality-verified eligible off-grid solar renewable energy systems PVOC Importation Guidelines & technical regulations for off-grid solar systems developed

## Slide 7: Project # 2: Liberia Renewable Energy Access Project – ongoing, < 10% complete.
Bidding document for HC electrification (1st 100 nos.) under review Planning documents for SHS deployment moderately completed Planning for mini-grid deployment through PPP

## Slide 8: Project Implementation Good Practice
Adhering to Safeguard requirements Progress elaboration of project plans Continuous engagement with stakeholders (Contractors, Consultant, beneficiaries, donor) Regular site inspection

## Slide 9: Issues and Challenges (challenges to effective project implementation)
Appreciable variations in feasibility study data & design values (*current) – causing delay in the finalization of the hydropower plant (project critical path) designs as balance between technical quality and economics is being sorted for to complete the hydropower plant within available budget. Occurrence of the COVID-19 crisis globally –stalled the mobilization of the Contractors Establishment of Letter of Credit (LC) in favor of the Contractors of the main contracts Bad road conditions from Zorzor to Voinjamin, especially during the rainy season – causing extreme difficulties in mobilizing materials to site.

## Slide 10
            Thanks